## Development Progress
CaratSense - Surplus Stock Intelligence Platform ¦ Development Progress
Sprint 1 & 2 ¦ April 2026 ¦ Developer: Shreyansh Kashyap
Date | Module | Task | Status | Details | Hrs
7-Apr-2026 | Project Setup | Repo setup, folder structure, Git init | Done | Backend (FastAPI) + Frontend (React/Vite) scaffold | 4
7-Apr-2026 | Database | Schema design - 12 tables | Done | Articles, Buyers, Sales, Purchases, StockEntries, Racks, Users, Tasks, Offers, FollowUps | 3
7-Apr-2026 | Backend | Auth system - JWT + geo-fencing | Done | PBKDF2 hashing, role-based permissions, 8hr token expiry | 3
8-Apr-2026 | Backend | Stock management API - full CRUD | Done | GET/POST/PUT/DELETE /stock/, aging auto-calc, rack meter tracking | 4
8-Apr-2026 | Backend | Buyer management API + dedup | Done | RapidFuzz matching, TF-IDF similarity, merge endpoint | 3
8-Apr-2026 | Backend | Sales & Purchase API | Done | CRUD, negotiation tracking, date filtering, summary stats | 3
9-Apr-2026 | ML Engine | Buyer-Product Matching (SVD) | Done | Collaborative filtering, buyer x article matrix, top-N recommendations | 4
9-Apr-2026 | ML Engine | Buyer Clustering (K-Means) | Done | 5 segments: VIP, Bulk, Regular, Occasional, Dormant | 2
9-Apr-2026 | ML Engine | Clearance Risk Prediction | Done | Sales velocity, days-to-sell, risk: critical/high/medium/low | 2
9-Apr-2026 | ML Engine | Basket Analysis - cross-sell | Done | Co-occurrence matrix, frequently bought together pairs | 2
10-Apr-2026 | Backend | Dashboard KPIs - summary, trends | Done | Weekly trends, aging breakdown, supplier scorecard (weighted) | 3
10-Apr-2026 | Backend | Warehouse API - rack CRUD | Done | Rack creation, capacity tracking, hall management | 2
10-Apr-2026 | Backend | Packing List Processor | Done | Quality auto-fill, rack suggestions, unknown article flagging | 3
10-Apr-2026 | Backend | QR codes + Export + EOD reports | Done | QR PNG + PDF labels, Excel exports, WhatsApp EOD format | 2
11-Apr-2026 | Backend | AI Chat - Gemini 2.5 Flash | Done | DB context injection, Hindi+English queries, streaming SSE | 3
11-Apr-2026 | Backend | Website Sync API | Done | API key auth, live-stock, auto-discounts at 60/90 days | 2
11-Apr-2026 | Backend | Follow-up reminder system | Done | 48hr auto-reminders, bilingual messages, max 3 then expire | 2
11-Apr-2026 | Data Import | Import all Excel data to DB | Done | 2,621 articles, 15,437 buyers, 52,900 sales, 511K purchases | 3
12-Apr-2026 | Frontend | Next.js 16 project - merged setup | Done | Shadcn UI, Tailwind 4, Zustand, React Query, Framer Motion | 3
12-Apr-2026 | Frontend | Landing page - marketing site | Done | Hero, Features, Product Preview, System Diagram, CTA, Footer | 3
12-Apr-2026 | Frontend | Login page - auth connected | Done | Email/password, geolocation, JWT storage, redirect | 2
12-Apr-2026 | Frontend | Dashboard layout + routing | Done | Sidebar, Cmd+K palette, module switching, page transitions | 2
13-Apr-2026 | Frontend | Smart Stock module | Done | Table + grid view, filters (type/grade/status/color), detail panel | 3
13-Apr-2026 | Frontend | Buyer Intelligence module | Done | 30 real buyers, profiles, purchase history, WhatsApp buttons | 3
13-Apr-2026 | Frontend | AI Matching module | Done | Stock-to-buyer matching, scores, WhatsApp pre-filled messages | 2
13-Apr-2026 | Frontend | Warehouse visualization | Done | 9 halls from real Excel, search by rack/goods, hall detail | 2
14-Apr-2026 | Frontend | Sales module with FIFO | Done | Create sale, oldest-lot-first, history, summary cards | 3
14-Apr-2026 | Frontend | AI Assistant (3-in-1 merged) | Done | Tabs: Buyer Matching + Insights & Analytics + AI Chat | 2
14-Apr-2026 | Frontend | Staff Tagging system | Done | Assign staff to stock, filter tagged/untagged/by person | 2
14-Apr-2026 | Frontend | Task Manager | Done | Create/complete tasks, priority, role-based assignment | 1
15-Apr-2026 | Frontend | Data Input (Excel + OCR) | Done | Packing processor (4 formats) + camera bale scan | 3
15-Apr-2026 | Frontend | Duplicate Detection UI | Done | Similarity slider, scan, merge - integrated in Buyers tab | 2
15-Apr-2026 | Frontend | Website Sync + Export | Done | Live stock view, Excel downloads for stock/buyers/sales | 2
15-Apr-2026 | Backend | Packing processor - 3 new formats | Done | WITH/WITHOUT GOWDEN, Google Sheet, bale-level parsing | 3
16-Apr-2026 | Data | Replace ALL mock data with real | Done | 5,734 stock, 742 buyers, 808 sales, 211 racks - zero fake | 3
16-Apr-2026 | Backend | Rack rules from real Excel | Done | 65 rules (was 20). Matches actual warehouse layout | 1
16-Apr-2026 | Frontend | Role-based sidebar | Done | Owner/Sales/Warehouse roles, auth-connected filtering | 1
16-Apr-2026 | Frontend | Framer Motion animations | Done | Page transitions, stagger, hover, slide panels, chat bubbles | 2
16-Apr-2026 | Integration | Backend + Frontend API wiring | Done | DataLoader, auth flow, AI chat to Gemini, export endpoints | 2
17-Apr-2026 | Frontend | Sidebar restructure (16 to 11) | Done | AI merged, Buyers+Dedup merged, OCR+Packing merged | 2
17-Apr-2026 | Data | Full DB import - SQLite | Done | 2,621 articles, 15,437 buyers, 52,900 sales, 4,990 stock | 2
17-Apr-2026 | Docs | Client requirements doc (27 items) | Done | Staff, buyer data, warehouse specs, Busy access, website | 1
17-Apr-2026 | Docs | Busy sync plan + bat script | Done | Auto-export + Python watcher + Task Scheduler guide | 1
17-Apr-2026 | Testing | E2E testing - login to all modules | In Progress | Backend :8001, Frontend :3000, verifying all API connections | 2
TOTAL |  | 44 tasks across 11 days |  |  | 105

## Module Status
Module / Feature | Status | Notes
Smart Stock Management | Done | CRUD, 6 types, quality grades, aging, color filter
Sales Module (FIFO) | Done | Create sale, oldest-lot-first, history, summary
Warehouse Visualization | Done | 9 halls, 211 racks, search, hall detail view
Buyer Intelligence | Done | 15,437 buyers, profiles, tags, WhatsApp
Duplicate Buyer Detection | Done | TF-IDF + fuzzy, threshold slider, merge
AI Buyer-Product Matching | Done | SVD collaborative filtering, top-N, scores
AI Insights & Analytics | Done | Dormant, clearance risk, clusters, aging
AI Chat (Gemini) | Done | Gemini 2.5 Flash, DB context, Hindi+English
Staff Stock Tagging | Done | Assign staff, filter tagged/untagged
Task Management | Done | Create/complete/reject, priority, roles
Data Input (Excel+OCR) | Done | 4 packing formats, camera scan, bale search
Website Sync | Done | Live stock API, auto-discounts, summary
Export System | Done | Stock/Buyers/Sales Excel downloads
Login + Auth + RBAC | Done | JWT, geo-fence, owner/sales/warehouse roles
Landing Page | Done | Marketing site, Framer Motion animations
WhatsApp Integration | Done | Pre-filled messages, wa.me links
QR Code Generation | Done | PNG + PDF labels (backend)
EOD Reports | Done | WhatsApp-formatted daily summary (backend)
Supplier Scorecard | Done | Weighted scoring from backend API
Busy Data Sync | Planned | Bat script + Python watcher, needs PC access
WooCommerce Sync | Planned | REST API connector, needs API keys from client